Product’s New Projects Policy

| Policy Name: | Product’s New Projects Policy |
| --- | --- |
| Policy Owner: | Mostafa Sami (Head of Product) |
| Date: | 10/9/2025 |
| Document Code | GR_PD_PL_01 |
| Revision: | 0.1 |

|  | Name | Title | Signature |
| --- | --- | --- | --- |
| Prepared by | Osama Adel | Group QA & Governance Manager |  |
| Reviewed by | Mostafa Sami | Head Of Product |  |
|  | Boubaker Rhimi | Chief Operations Officer (COO) |  |
|  | Ahmed Hassan | Chief Strategy Officer (CSO) |  |
| Approved by | AbdulAziz Alsenan | Chief Executive Officer (CEO) |  |

Table of Contents

1.	Purpose	3

2.	Scope	3

3.	Definitions	3

4.	Product Projects Handling Mechanism	4

4.1	Ideation:	4

4.2	Prototyping:	4

4.3	Business Modeling	5

4.4	Business Modeling Validation	6

4.5	Project Planning	6

4.6	Project Implementation	7

4.7	Project Monitoring	8

4.8	Project Delivery & Closing	8

4.9	Continuous Improvement	9

5.	Summary of Projects RACI Matrix	10

6.	Handoff Protocols	11

# Purpose

The purpose of this policy is to establish a standardized, transparent, and efficient framework for managing projects across inside PetroApp. This ensures a cohesive workflow from the initial concept to post-launch improvements, clarifying roles and responsibilities, defining key deliverables for each stage, and promoting proactive, cross-functional collaboration.

# Scope

The policy applies to the entire end-to-end lifecycle of all new product initiatives, feature developments, and significant enhancements within the company. They serve as the primary reference for all teams involved in the project lifecycle.

# Definitions

Based on the project management lifecycle provided, a project can be defined as a structured initiative that moves from concept to delivery with the goal of creating business value which includes one or more of the following:

- Product Development: A project is centered around creating a new product or solution.

- Market Development: Adapting and launching the product for a new customer segment or geographical area.

# Product Projects Handling Mechanism

## Ideation:

## Objective: To identify, define, and perform a preliminary validation of new market opportunities and product concepts.

## Accountable Department: Product Department.

## Guideline: The Product Department is accountable for identifying and validating new opportunities and should encourage collaborative brainstorming with cross-functional input to align ideas with market needs.

## Key Deliverables:

## Problem Statement Definition.

## Market Opportunity Analysis.

## Initial High-Level Solution Concept.

## User Persona & Needs Identification.

## Competitive Landscape Analysis.

## Preliminary Feasibility Assessment.

## RACI:

## Responsible: Tech and all relevant departments as needed.

## Accountable: Product.

## Consulted: Marketing, Sales, Customer Experience/Account Management.

## Informed: Strategy.

## Prototyping:

Objective: To develop low-fidelity models of the proposed solution to gather user feedback and conduct initial technical review.

- Accountable Department: Product Department.

- Guideline: The Product Department is accountable for creating a model representation of the solution for feedback.

- Key Deliverables:

  - User Flows & Wireframes.

  - Low-Fidelity Prototypes.

  - User Testing & Feedback.

  - Technical Feasibility Check.

  - Initial Tech Stack Review.

- RACI:

  - Responsible: Tech and all relevant departments as needed.

  - Accountable: Product.

  - Consulted: Marketing, Sales, Customer Experience/Account Management.

  - Informed: Strategy.

## Business Modeling

Objective: To create a comprehensive document outlining the project's value proposition, financial viability, and potential risks.

- Accountable Departments: Product Department.

- Guideline: The Product Department is accountable for creating comprehensive business modeling and must make sure that the solution hits the opportunity or eliminates the risk.

- Key Deliverables:

  - Opportunity Analysis.

  - Value Proposition.

  - Target Market & Revenue Model.

  - Risk Assessment.

  - Pricing Strategy.

- RACI:

  - Responsible: All departments as needed.

  - Accountable: Product.

  - Consulted: Strategy & Finance.

  - Informed: Marketing + Sales + Gov Team.

## Business Modeling Validation

Objective: To ensure project feasibility and align with all stakeholders and securing a "Go" decision from projects committee.

- Accountable Department: Strategy.

- Guideline: The Strategy department is accountable for validating the business model aspects with all relevant stakeholders, and to obtain final approval from the new project committee (CxOs/Department Heads and CEO)

- Key Deliverables:

  - Strategic Fit & Legal Checks

  - Financials & Market Validations

  - Go Decision / Study iteration

- RACI:

  - Responsible: All departments as needed.

  - Accountable: Strategy.

  - Consulted: Any relevant stakeholder.

  - Informed: Marketing, Sales, Governance Team.

## Project Planning

Objective: To develop a detailed and integrated master plan that will guide project execution.

- Accountable Departments: Strategy, Product, Tech.

- Guideline: The Strategy, Product, and Tech departments are accountable for developing an integrated master plan to guide execution, ensuring resources availability and should coordinate across teams using the master plan as the single source of truth.

- Key Deliverables:

  - Product Roadmap & Success Criteria.

  - Tech Sprint Plan.

  - Non-Tech Plan.

  - Integrated Master Plan (coordinated by Strategy).

- RACI:

  - Responsible: All departments as needed.

  - Accountable (Roadmap/Deliverables): Product.

  - Accountable (Sprint Plan): Tech Team.

  - Accountable (Integrated Plan): Strategy.

  - Consulted: HR

  - Informed: Finance, Governance Team.

## Project Implementation

Objective: To execute the project plan, build the product, and manage cross-functional activities.

- Accountable Departments: Tech Team and other involved functions.

- Guideline: The Tech department and other involved functions are accountable for executing the project plan and should use daily syncs to manage dependencies, with the Product team validating sprint outcomes

- Key Deliverables:

  - Sprint Execution.

  - Cross-Department Meetings.

  - Testing & QA.

  - Change Requests.

- RACI:

  - Responsible: All departments as needed.

  - Accountable (Product Development): Tech Team.

  - Accountable (Cross-Functional Deliverables): Involved Functions.

  - Consulted: Product

  - Informed: HR, Commercial Teams.

## Project Monitoring

Objective: To track project progress against the plan, monitor risks and budget, and provide regular status reports.

- Accountable Department: Strategy.

- Guideline: The Strategy department is accountable for tracking progress and monitoring risks and should use dashboards to resolve issues proactively, leveraging clear ownership to prevent delays.

- Key Deliverables:

  - Deliverables Tracking.

  - Risk & Budget Monitoring.

  - Reporting.

- RACI:

  - Responsible: Involved Functions.

  - Accountable: Strategy.

  - Consulted: Product.

  - Informed: All departments as needed.

## Project Delivery & Closing

Objective: To successfully launch the product, hand it over to operational teams, and conduct a project retrospective.

- Accountable Departments: Product, Strategy.

- Guideline: The Product and Strategy departments are accountable for successfully launching the product and closing the project and must document outcomes and ensure operations can support what is delivered.

- Key Deliverables:

  - Release Checklist.

  - Handover to Operations, Sales, and Customer Success teams.

  - Launch Plan.

  - Retrospective.

- RACI:

  - Responsible: Governance Team, Involved Functions.

  - Accountable: Product, Strategy.

  - Accountable (Retrospective): All.

  - Consulted: Sales, Operations, Tech.

## Continuous Improvement

Objective: To establish a systematic process for gathering feedback and planning future iterations.

- Accountable Department: Product Team.

- Guideline: The Product Team is accountable for establishing a systematic process for gathering feedback for future iterations and should embed feedback loops in the culture through regular retrospectives and product reviews.

- Key Deliverables:

  - Feedback Loop.

  - Iteration Roadmap.

  - Efficiency Reports.

  - Customer Support Input.

- RACI:

  - Responsible: Governance Team, Involved Departments.

  - Accountable: Product Team.

  - Consulted: Tech, Customer Experience/Account Management, Marketing.

  - Informed: Strategy.

# Summary of Projects RACI Matrix

| Phase | Key Milestones (Deliverables) | Accountable Department | RACI Matrix | Comments |
| --- | --- | --- | --- | --- |
| Ideation | 1. Problem Statement Definition 2. Market Opportunity Analysis 3. Initial Solution Concept (High-level) 4. User Persona & Needs Identification 5. Competitive Landscape Analysis 6. Preliminary Feasibility Assessment | Product Department | R: Tech + All as per needed A: Product C: Marketing, Sales, CX I: Strategy | Encourage collaborative brainstorming with cross-functional input. Involve Sales and Marketing early to align ideas with market needs. |
| Prototyping | 1. User Flows & Wireframes 2. Low-Fidelity Prototypes 3. User Testing & Feedback 4. Technical Feasibility Check 5. Initial Tech Stack Review | Product Department | R: Tech + All as per needed A: Product C: Marketing, Sales, CX I: Strategy | Ensure tight feedback loops. Focus on learning, not production builds. |
| Business Modeling | 1. Opportunity Analysis 2. Value Proposition 3. Target Market & Revenue Model 4. Risk Assessment 5. Pricing Strategy | Product Department | R: All as per needed A: Product C: Strategy + Finance I: Marketing + Sales + Gov Team | Determine the financial and market model, risk assessment and pricing startegy |
| Business Modeling Validation | 1. Strategic Fit & Legal Checks 2. Financials & Market Validations 3. Go Decision / Study iteration | Strategy | R: All as per needed A: Strategy C: Any relevant stakeholder I: Marketing + Sales + Gov Team | - Strategy ensures project feasibility and aligning All stakeholders before proceeding. - Strategy submits the validated case to the committee for final approval (CEO-CxO/Heads-Relevant Country Manager) |
| Project Planning | 1. Product Roadmap, Success Criteria 2. Sprint Plan 3. Non-Tech Plan 4. Integrated Master Plan | Strategy, Product, Tech | R: All as per needed A (Roadmap / Deliverables planning): Product A (Sprint Plan) : Tech A (Cross Functions / Integrated Plan) : Strategy C: HR I: Finance+ Gov team | Coordinate across teams. Use a master plan as the single source of truth. |
| Project Implementation | 1. Sprint Execution 2. Cross-Dept Meetings 3. Testing & QA 4. Change Requests | Tech + involved Functions | R: All as per needed A (Product Development) : Tech A ( Cross Function Deliverables) : involved Functions C: Product I: HR, Commercial Teams | Daily syncs to manage dependencies. Product validates sprint outcomes. |
| Project Monitoring | 1. Deliverbales Tracking 2. Risk & Budget Monitoring 3. Reporting | Strategy | R: involved Functions A : Strategy C : Product: I: All as per needed | Use dashboards. Resolve issues proactively. Clear ownership helps prevent delays. |
| Project Delivery & Closing | 1. Release checklist 2. Handover to Ops/Sales/CS Launch plan 3. Retrospective | Product + Strategy | R: Gov Team + involved Functions A: Product + Strategy C: Sales, Ops, Tech, I: All | Document and celebrate wins. Ensure operations can support what's delivered. |
| Continuous Improvement | 1. Feedback loop 2. Iteration roadmap 3. Efficiency reports 4. Customer support input | Product Team | R: Gove Team + involved dept. A: Product C: Tech, CS, Marketing I: Strategy | Embed feedback loops in culture. Regular retros and product reviews are key. |

# Handoff Protocols

| From → To | Handoff Document / Action | Responsibility | Comments |
| --- | --- | --- | --- |
| Ideation → Prototyping | Idea validation brief + target personas | Product | Formal approval from Product Lead |
| Prototyping → Business Modeling | BRD + Validated prototype + tech feasibility summary + high level feasibility | Product + Tech | Internal review session |
| Business Modeling → Business Modeling Validation | Complete business model considering all project aspect | Product | Sign-off by Product |
| Business Modeling Validation → Project Planning | Validated business model or Study iteration Approved business model by new project approval committee | - Strategy → Alignment of business model validation with all stakeholders - Strategy → Obtaining approval from the concerned project committee before project kickoff | Strategy and Product ensure project kickoff |
| Planning → Implementation | Integrated plan (Sprints + Deliverables) | Product + Strategy + Tech | Kickoff with all departments |
| Implementation → Monitoring | Sprint plans, dashboards, and milestone dates | Tech + Strategy + Product | Ensure real-time updates |
| Monitoring → Delivery | Launch checklist, stakeholder signoffs | Strategy + Product | Pre-launch review |
| Delivery → Continuous Improvement | Retrospective report + backlog of future improvements | Product | Create post-mortem template |